Arc Transit Systems

Agile-Kanban Progress Tracker

Transit Operations Command and Fleet Intelligence Platform

# 1. Project Overview

| Field | Current Value |
| --- | --- |
| Project Name | Arc Transit System |
| Development Method | Agile-Kanban; with two-week progress reviews |
| Target Duration | 12 weeks / 3 months (Estimated) |
| Target Start Date | June 15, 2026 |
| Target End Date | August 16, 2026 (Estimated) |
| Current Development Stage | Week 7 - Driver and Route |
| Current Status | In Progress |
| Technology Stack Scope | Vaadin, Spring Boot, Spring Modulith, PostgreSQL, Flyway, session security, and Docker; simulated or manually submitted operational data |
| Project Owner | Chuckz Española |

# 2. Kanban Workflow

| State | Meaning | How it is used |
| --- | --- | --- |
| Planned | Approved work retained for a later week or iteration. | Select when its timing and dependencies are appropriate. |
| Ready | Defined work with a clear task, expected result, and known dependencies. | May be started without further design clarification. |
| In Progress | Work currently being designed, implemented, or documented. | Keep active work limited so the current task can reach completion. |
| Testing and Review | Work being checked through tests, manual validation, or technical review. | Return it to In Progress when corrections are required. |
| Completed | The expected result has been produced and verified. | Record the completion date and the relevant result, commit, test, or document update. |
| Blocked | Work that cannot continue because of a technical issue, unresolved dependency, or required decision. | Record the blocker and the next action needed to resume work. |

# 3. Project Objectives

| ID | Target | Milestone | Expected Accomplishment | Status |
| --- | --- | --- | --- | --- |
| Objective 1 | Week 2 | Requirements and Architecture | Scope, requirements, user flows, modules, security approach, and architecture documented. | Completed |
| Objective 2 | Week 4 | Database and Service Design | ERDs, data types, constraints, indexes, and application-service contracts completed. | Completed |
| Objective 3 | Week 6 | Application Foundation | Runnable application with PostgreSQL, Flyway, session login, role checks, audit support, and first Fleet workflow. | Completed |
| Objective 4 | Week 8 | Core Operations | Fleet, Driver, Route, and Dispatch workflows operate through Vaadin. | Planned |
| Objective 5 | Week 10 | Operations Dashboard | Incident, Maintenance, status updates, dashboard metrics, analytics, and route presentation completed. | Planned |
| Objective 6 | Week 12 | Final Release | Testing, benchmarks, Docker deployment, README, screenshots, and final documentation completed. | Planned |

# 4. Full Weekly Work Plan

| Week | Main Focus | Planned Work | Expected Result | Status |
| --- | --- | --- | --- | --- |
| Week 1 | Scope and requirements | Finalize objectives, account categories, functional and non-functional requirements, and exclusions. | Approved scope and requirements. | Completed |
| Week 2 | Architecture and UX design | Finalize user flows, technology choices, module responsibilities, security approach, and architecture diagrams. | Architecture and UX design baseline. | Completed |
| Week 3 | Database design | Complete ERDs, tables, columns, PostgreSQL types, keys, relationships, constraints, indexes, and audit fields. | Database design ready for Flyway and JPA mapping. | Completed |
| Week 4 | Application-service contracts | Define module interfaces, commands, queries, view models, authorization, transactions, errors, and internal events. | Service contracts aligned with requirements and database design. | Completed |
| Week 5 | Application foundation | Create the Maven project, dependencies, Spring Boot configuration, module packages, PostgreSQL Docker service, Flyway baseline, and Vaadin shell. | Runnable project with verified modules and database connection. | Completed |
| Week 6 | Security, audit, and Fleet | Implement session login, roles, audit foundation, account seed data, and the first Fleet workflow. | Authenticated application with role-aware navigation and Fleet persistence. | Completed |
| Week 7 | Driver and Route | Implement driver records, license checks, routes, ordered stops, schedules, validation, and module views. | Driver and Route workflows available through Vaadin. | In Progress |
| Week 8 | Dispatch and assignment | Implement availability checks, vehicle-driver-route assignment, conflicts, dispatch lifecycle, and audit events. | Dispatch workflow rejects invalid or overlapping assignments. | In Progress |
| Week 9 | Incident and Maintenance | Implement incident reporting, resolution, maintenance scheduling, work status, and vehicle availability changes. | Incident and Maintenance workflows persist and affect operations correctly. | Planned |
| Week 10 | Status and analytics | Implement fleet status submissions, dashboard cards, summaries, filters, route presentation, and audit views. | Operations dashboard uses real persisted data. | Planned |
| Week 11 | Testing and benchmarks | Complete unit, module, integration, security, and browser tests; run planned performance measurements. | Test results and measured benchmark report. | Planned |
| Week 12 | Deployment and release | Complete Docker startup, cloud-VM deployment, defect correction, README, screenshots, and final documentation. | Reproducible final release and portfolio package. | Planned |

# 5. Week Status

## Week 1 - Scope and Requirements

| ID | Area | Task | Work Details | Expected Result | Status | Notes / Date |
| --- | --- | --- | --- | --- | --- | --- |
| W1-01 | Project Definition | Define project purpose and objectives | Write the system purpose, target users, development intent, and measurable project objectives. | Clear project purpose and objective statement. | Completed | Monday - June 15, 2026 Drafted the project purpose, intended users, development goals, and initial measurable objectives for Arc Transit System. |
| W1-02 | Scope | Finalize Version 1 boundaries | Document included operational capabilities and excluded features such as GPS, mobile, payment processing, and microservices. | A controlled and achievable Version 1 scope. | Completed | Wednesday - June 17, 2026 Defined the draft prototype system scope and separated the essential transit-operation features from GPS tracking, mobile development, fare processing, and microservices. |
| W1-03 | Requirements | Write functional requirements | Define expected behavior for Fleet, Driver, Route, Dispatch, Incident, Maintenance, Dashboard, security, and audit functions. | Major system capabilities are covered by buildable requirements. | Completed | Thursday - June 18, 2026 Documented the main functional requirements for Fleet, Driver, Route, Dispatch, Incident, Maintenance, Dashboard, security, and audit functions. |
| W1-04 | Requirements | Write non-functional requirements | Define measurable targets for performance, security, logging, Docker setup, tests, and dependency checks. | Requirements can be verified later through tests or measurements. | Completed | Saturday - June 20, 2026 Added measurable non-functional requirements covering performance, security, validation, logging, testing, Docker deployment, and dependency checks. |
| W1-05 | Trade-offs | Document excluded features and approach | Explain why excluded features are not part of Version 1 and state the practical substitute used by the prototype. | Scope decisions are understandable and technically defensible. | Completed | Sunday - June 21, 2026 Completed the trade-off analysis and reviewed the Week 1 scope to confirm that the planned system remained achievable within twelve weeks. |

Monday - June 15, 2026

- Defined Arc Transit System as an internal transit-operations platform rather than a public passenger application.

- Wrote the initial project purpose, intended users, development goals, and expected portfolio value.

- Clarified that the system would use manually submitted or simulated transit data instead of claiming live operational data.

- Established the initial twelve-week development target.

Wednesday - June 17, 2026

- Reviewed the original concept and reduced the scope after identifying that GPS tracking and a mobile driver application would require significantly more development time.

- Removed live vehicle telemetry from Version 1.

- Retained fixed routes, route stops, status updates, and dispatch operations as realistic alternatives.

- Defined the main Version 1 boundaries to prevent the project from expanding into an IoT or mobile platform.

Thursday - June 18, 2026

- Drafted the functional requirements for Fleet, Driver, Route, Dispatch, Incident, Maintenance, Dashboard, Security, and Audit functions.

- Defined the main actions available to System Administrators and Operations Staff.

- Clarified that drivers are managed operational records and are not authenticated application users.

- Reviewed the requirements to ensure that each major feature could later be connected to a database table and application-service operation.

Saturday - June 20, 2026

- Added non-functional requirements for page performance, search response time, login performance, security, validation, logging, Docker deployment, and automated testing.

- Converted general claims such as “fast” and “secure” into measurable targets that can be tested after implementation.

- Added the requirement that critical dependency vulnerabilities must be resolved before the final release.

- Defined PostgreSQL Testcontainers as the authoritative database environment for integration tests.

Sunday - June 21, 2026

- Completed the trade-off analysis for GPS, mobile development, microservices, payment processing, live authority deployment, advanced analytics, and multi-tenant operation.

- Explained the practical substitute used for each excluded feature.

- Reviewed the complete Week 1 requirements and scope for contradictions.

- Confirmed that the project remained achievable as a solo developer portfolio system.

Weekly Result

- Completed the Version 1 scope, objectives, functional requirements, non-functional requirements, and trade-off analysis.

- Produced a clear project boundary that protects the twelve-week development plan from unnecessary feature expansion.

Work Carried Forward

- User-flow design and architecture decisions were moved into Week 2.

## Week 2 - Architecture and UX Design

| ID | Area | Task | Work Details | Expected Result | Status | Notes / Date |
| --- | --- | --- | --- | --- | --- | --- |
| W2-01 | UX/UI | Finalize account categories | Define SYSTEM_ADMIN and OPERATIONS_STAFF responsibilities and confirm that drivers remain operational records. | Access categories align with security and database design. | Completed | Monday - June 22, 2026 Finalized the SYSTEM_ADMIN and OPERATIONS_STAFF account categories. Confirmed that drivers remain operational records rather than authenticated users. |
| W2-02 | UX/UI | Finalize prototype and user flows | Review dashboard, authentication, fleet, route, incident, terminal-status, and analytics navigation flows. | User flows match Version 1 modules and permissions. | Completed | Tuesday - June 23, 2026 Reviewed the prototype dashboard and aligned the authentication, fleet, route, terminal-status, incident, and analytics user flows with the Version 1 scope. |
| W2-03 | Architecture | Define runtime architecture | Document Browser to Vaadin/Spring Boot to Spring Modulith modules to PostgreSQL. | Runtime flow is clear and has no JavaFX or JWT contradiction. | Completed | Thursday - June 25, 2026 Defined the runtime flow from the browser and Vaadin interface through Spring Boot, Spring Modulith modules, and PostgreSQL. |
| W2-04 | Architecture | Define technologies and module responsibilities | List each technology, how it is used, and the records or output owned by every module. | Architecture components have clear responsibilities. | Completed | Thursday - June 25, 2026 Documented the responsibility of each technology and matched every system module to its primary records and outputs. |
| W2-05 | Architecture | Record architecture decisions | Compare selected approaches with practical alternatives for architecture, database, UI, security, data access, events, build, deployment, and testing. | Major design choices are explained without unnecessary infrastructure. | Completed | Saturday - June 27, 2026 Recorded the main architecture decisions and compared the selected approaches with realistic alternatives without adding unnecessary infrastructure. |
| W2-06 | Performance | Define benchmark targets | Set planned targets for dashboard load, login, fleet search, and route lookup using simulated datasets. | Performance claims will be based on measured results after implementation. | Completed | Sunday - June 28, 2026 Defined the planned dashboard, login, fleet-search, and route-lookup performance targets. Completed the first two-week project review. |

Monday - June 22, 2026

- Reduced the original role structure to two account categories: SYSTEM_ADMIN and OPERATIONS_STAFF.

- Defined which modules and actions each account category can access.

- Confirmed that driver records remain separate from authenticated staff accounts.

- Updated the role descriptions to match the intended Spring Security configuration.

Tuesday - June 23, 2026

- Reviewed the existing dashboard prototype and identified the main operational navigation areas.

- Updated the user-flow diagrams for authentication, Fleet, Route, Terminal Status, Incidents, and Analytics.

- Checked that the flow diagrams matched the current Version 1 features and did not imply GPS or mobile functionality.

- Added validation, access-denied, retry, database-update, and audit-log paths where appropriate.

Thursday - June 25, 2026

- Defined the runtime architecture as:

- Web Browser

- Vaadin and Spring Boot

- Spring Modulith Modules

- Spring Data JPA or JDBC

- PostgreSQL

- Removed the previous JavaFX client and JWT API design because it no longer matched the selected Vaadin architecture.

- Defined the responsibility of Java, Spring Boot, Spring Modulith, Vaadin, Spring Security, PostgreSQL, Flyway, Maven, and Docker Compose.

- Matched each system module to its main records and expected outputs.

Saturday - June 27, 2026

- Documented the decision to use a Spring Modulith modular monolith instead of microservices.

- Compared PostgreSQL with MySQL, MongoDB, and H2.

- Compared Vaadin with React, Angular, and Thymeleaf.

- Selected Maven instead of Gradle because the project uses a standard Spring Boot build and does not require a custom build process.

- Selected Spring Security session authentication instead of JWT because Vaadin maintains the application session on the server.

- Confirmed that internal events would use Spring application events rather than Kafka or RabbitMQ.

Sunday - June 28, 2026

- Defined planned benchmark targets for dashboard load time, login performance, fleet search, and route lookup.

- Separated benchmark targets from actual results so the documentation would not claim measurements that had not yet been performed.

- Defined demo and benchmark datasets for later testing.

- Completed the first two-week project review covering Weeks 1 and 2.

Weekly Result

- Completed the application architecture, technology selection, module responsibilities, security direction, user flows, and benchmark targets.

- Replaced the outdated JavaFX and JWT architecture with a consistent Vaadin and Spring Boot design.

Work Carried Forward

- Database entities and relationships were moved into Week 3.

## Week 3 - Database Design

| ID | Area | Task | Work Details | Expected Result | Status | Notes / Date |
| --- | --- | --- | --- | --- | --- | --- |
| W3-01 | Database | Create Core Operations ERD | Model Fleet, Driver, Route, Dispatch, Fleet Status, Incident, and Maintenance relationships. | Operational records and foreign-key relationships are visible. | Completed | Monday - June 29, 2026 Created the Core Operations ERD covering Fleet, Driver, Route, Dispatch, Fleet Status, Incident, and Maintenance relationships. |
| W3-02 | Database | Create Security and Audit ERD | Model app_users, roles, user_roles, and audit_log separately from operational records. | Authentication and audit data are clearly separated from transit records. | Completed | Wednesday - July 1, 2026 Created the separate Security and Audit ERD for application users, roles, user-role assignments, and audit records. |
| W3-03 | Database | Define schema and table ownership | Map each table to its Spring Modulith module inside the single arc PostgreSQL schema. | Every table has a clear owning module and purpose. | Completed | Thursday - July 2, 2026 Assigned every database table to its responsible Spring Modulith module while retaining one PostgreSQL application schema. |
| W3-04 | Database | Complete data dictionary | Document columns, PostgreSQL types, nullability, defaults, keys, and field meaning. | Flyway and JPA implementation can follow the documented physical design. | Completed | Saturday - July 4, 2026 Completed the data dictionary with PostgreSQL data types, nullability, defaults, keys, field meanings, and important implementation notes. |
| W3-05 | Database | Define constraints and indexes | Document unique keys, foreign keys, check constraints, optimistic locking, soft archive fields, and query-supporting indexes. | Data integrity and planned searches are supported by the schema. | Completed | Saturday - July 4, 2026 Documented unique constraints, foreign keys, status checks, archive fields, optimistic locking, and the indexes required by expected searches. |
| W3-06 | Database | Plan Flyway migrations | Order schema, reference data, operational tables, indexes, constraints, and demo data into versioned migrations. | Database creation can be reproduced from an empty PostgreSQL instance. | Completed | Sunday - July 5, 2026 Planned the Flyway migration sequence for the schema, reference records, operational tables, indexes, constraints, and demonstration data. |

Monday - June 29, 2026

- Created the Core Operations ERD.

- Defined the main relationships between Fleet Units, Drivers, Routes, Route Stops, Route Schedules, Dispatch Assignments, Fleet Status Updates, Incidents, and Maintenance Records.

- Identified dispatch_assignments as the record connecting a vehicle, driver, route schedule, and service date.

- Reviewed the relationships to avoid unnecessary duplicate data.

Wednesday - July 1, 2026

- Created a separate Security and Audit ERD.

- Defined app_users, roles, user_roles, and audit_log.

- Separated authenticated staff accounts from driver records.

- Confirmed that roles would be stable reference records created through Flyway migrations.

Thursday - July 2, 2026

- Assigned each database table to its responsible Spring Modulith module.

- Kept one PostgreSQL application schema named arc.

- Rejected a schema-per-module design because it would add physical separation without practical value for one application.

- Clarified that table ownership is logical and enforced through module boundaries in the Java code.

Saturday - July 4, 2026

- Completed the database data dictionary.

- Defined PostgreSQL types, nullability, defaults, primary keys, foreign keys, audit fields, and field purposes.

- Selected BIGINT IDENTITY for entity primary keys.

- Selected TIMESTAMPTZ for recorded instants.

- Used VARCHAR values with named CHECK constraints for workflow states so state changes remain manageable through Flyway.

- Defined indexing for usernames, plate numbers, route codes, foreign keys, statuses, and expected search paths.

Sunday - July 5, 2026

- Planned the Flyway migration order.

- Separated schema creation, reference data, operational tables, indexes, constraints, and demonstration data into ordered migration groups.

- Confirmed that Hibernate automatic schema updates would not be used.

- Reviewed the database design against the functional requirements and application modules.

Weekly Result

- Completed the two ERDs, module ownership table, data dictionary, indexes, constraints, physical database conventions, and migration plan.

- Produced a database design that can be translated directly into Flyway SQL and JPA mappings.

Work Carried Forward

- Application-service contracts were moved into Week 4.

## Week 4 - Service Contracts

| ID | Area | Task | Work Details | Expected Result | Status | Notes / Date |
| --- | --- | --- | --- | --- | --- | --- |
| W4-01 | Services | Define module service boundaries | Describe the public application-service interface for each module and prevent cross-module repository access. | Vaadin views have defined entry points into the backend. | Completed | Monday - July 6, 2026 Defined the application-service boundary for each module and established that Vaadin views must not directly access repositories. |
| W4-02 | Services | Define commands, queries, and view records | Document input commands, read queries, and immutable results used by the UI. | UI and domain objects remain separated. | Completed | Wednesday - July 8, 2026 Documented the commands, queries, and immutable view records used between the Vaadin interface and application services. |
| W4-03 | Security | Define authorization and transaction boundaries | Assign permitted roles to service operations and identify where transactions begin and end. | Security and consistency rules are applied at service boundaries. | Completed | Thursday - July 9, 2026 Assigned the permitted roles and transaction boundaries for state-changing application-service operations. |
| W4-04 | Errors | Define validation and error handling | Document field validation, not-found, conflict, stale update, access denied, and unexpected error behavior. | User-facing messages and technical logs have separate purposes. | Completed | Thursday - July 9, 2026 Defined validation, not-found, conflict, stale-update, access-denied, and unexpected-error handling for the user interface and server logs. |
| W4-05 | Events | Define internal module events | List domain events used for decoupled notifications between modules without external message brokers. | Module communication remains inside the modular monolith. | Completed | Saturday - July 11, 2026 Listed the internal application events required for communication between modules without introducing an external message broker. |
| W4-06 | Scope Alignment | Keep Version 1 services internal | Remove speculative external REST API design and keep the current UI-to-service flow inside Vaadin and Spring Boot. | Service design matches the implemented Version 1 architecture. | Completed | Sunday - July 12, 2026 Removed the speculative external API design and aligned the service documentation with the internal Vaadin-to-application-service architecture. Completed the second two-week review. |

Monday - July 6, 2026

- Defined the public application-service boundary for every system module.

- Established that Vaadin views call application services rather than repositories.

- Prevented direct cross-module repository access.

- Identified the main commands, queries, and returned view records required by the UI.

Wednesday - July 8, 2026

- Defined command objects for state-changing operations.

- Defined query objects for searches, filtering, and dashboard reads.

- Defined immutable view records for returning data to the Vaadin interface.

- Kept JPA entities internal to their owning modules.

Thursday - July 9, 2026

- Assigned authorization rules to the service operations.

- Defined which operations require SYSTEM_ADMIN and which are available to OPERATIONS_STAFF.

- Defined transaction boundaries for create, update, archive, assignment, incident, and maintenance operations.

- Documented validation, not-found, conflict, stale-update, access-denied, and unexpected-error behavior.

Saturday - July 11, 2026

- Defined the internal events used between modules.

- Added events for assignment changes, fleet-status changes, incident reporting, maintenance status, and other cross-module notifications.

- Checked that event use would not replace direct application-service calls where an immediate result is required.

- Confirmed that Kafka and RabbitMQ were unnecessary because all modules operate inside one application process.

Sunday - July 12, 2026

- Removed the speculative Future External API section.

- Updated the service design so it describes only the actual Version 1 Vaadin-to-application-service flow.

- Reviewed the database, service contracts, roles, error model, and module boundaries for consistency.

- Completed the second two-week project review covering Weeks 3 and 4.

- Prepared the project for implementation beginning in Week 5.

Weekly Result

- Completed the application-service contracts, authorization boundaries, transaction rules, error handling, and event catalog.

- Aligned the backend design with the Vaadin modular-monolith architecture.

Work Carried Forward

- Project generation, Docker configuration, Flyway setup, and the Vaadin shell moved into Week 5.

## Week 5 - Draft Test Template Setup

| ID | Area | Task | Work Details | Expected Result | Status | Notes / Date |
| --- | --- | --- | --- | --- | --- | --- |
| W5-01 | Project Setup | Create initial draft template | Generated the base project and configured initial tools. | A Template Draft of the System | Completed | Monday - July 13, 2026 Created the first working project template and installed the required development tools |

Monday - July 13, 2026

- Created and tested the first working draft template of Spring Boot project.

- Installed and configured the required development tools.

  - PostgreSQL 17

  - Java JDK 21

  - Antigravity IDE

  - Docker Desktop (and the Debian container: postgres:17-bookworm)

  - # debian.sh --arch 'amd64' out/ 'bookworm' '@1783900800'

## Week 6 - Additional Setup, Authentication, and SQL Schema

| ID | Area | Task | Work Details | Expected Result | Status | Notes / Date |
| --- | --- | --- | --- | --- | --- | --- |
| W6-03 | Project Setup | Initialize the Maven Java Application | Initialize the actual Arc Transit System repository and base Spring Boot application using Spring Boot Initializr. | Initialize the actual project. | Completed | Wednesday - July 22, 2026 Created Arc Transit System project using Spring Initializr. Configured the project with Java 21, Spring Boot 4.1.0, Maven, and the Maven Wrapper. Used a temporary project-specific JAVA_HOME configuration without changing the permanent system-wide Java version, verifying mvnw.cmd -version. Initialized local Git repository. Ran the generated Spring Boot automated test and confirmed that the application context loaded successfully with no test failures. |
| W6-04 | Frontend | Implement Vaadin Dependency on pom.xml | Configure Vaadin application foundation and add initial dashboard route. | Implement the Vaadin UI on the project | Completed | Thursday - July 23, 2026 Added the Vaadin dependencies on pom.xml. Created a simple dashboard route to establish a server-side rendered user interface. |
| W6-04 | Documentation | Update Project Status | Record progress in development notes and add project README. | Update the current progress of the project | Completed | Thursday - July 23, 2026 Recorded the progress via edit.md and README.md to ensure development process are tracked. Updated edit.md status to reflect the completion and verification of the entire development process. |
| W6-04 | Database | Database Configuration through Docker Compose, implement PostgreSQL Dependency on pom.xml | Configure PostgreSQL data connection via Docker Compose (.yaml) and connect Java application. | Connect the Java Application to the PostgreSQL Database running via Docker Desktop | Completed | Thursday - July 23, 2026 Added the PostgreSQL dependencies on the pom.xml and configured the PostgreSQL to run on a Docker Desktop container via Docker Compose. |
| W6-04 | Database | SQL schema and Flyway Configuration | Configure Flyway-managed database schemas: - V1__create_fleet_units.sql | Created the First version of database Schema SQL layout and Implemented the Flyway Configuration | Completed | Thursday - July 23, 2026 Configured Flyway-managed database schemas, establishing a strict, version-controlled migration. |
| W6-04 | Architecture | Implement Spring Modulith Dependency on pom.xml | Implement Spring Modulith dependency and organize codebase layout. | Set the project to utilize Modular Monolith Architecture | Completed | Thursday - July 23, 2026 Implemented Spring Modulith dependencies and established the modular modulith folder layout in the codebase, strictly isolating the application into distinct, cohesive business capability packages. |
| W6-04 | Database | Auth SQL Schema | Create database SQL schema for authentication and user roles. - V2__create_authentication_tables.sql | Schema verified in properly implemented int the PostgreSQL database. | Completed | Thursday - July 23, 2026 Designed and implemented the database SQL schema, for authentication and user roles. Implemented SQL constraints for lowercase uniqueness and fixed enum-style role mappings on the database. |
| W6-04 | Frontend | Auth Login Logic Component | Create and debug the auth login component. | Login view renders securely. | Completed | Thursday - July 23, 2026 Created and debugged the initial working authentication login component, ensuring the Vaadin interface correctly interfaces with the Spring Security dependency. |
| W6-05 | Setup | Administrator Bootstrap | Implement DevAdminSeeder to seed the default admin account on startup under dev profile. | Set Admin account automatically in Database. | Completed | Saturday - July 25, 2026 Implemented the DevAdminSeeder to automatically bootstrap the default admin account securely via JdbcTemplate. |
| W6-05 | Backend | Authentication Logic | Implement auth logic with robust Java 21 records and strict Enum evaluations. | Spring Security correctly evaluates status. Cleaner, lesser boilerplate in code. | Completed | Saturday - July 25, 2026 Refactored the Authentication module's public API to utilize immutable Java 21 records for thread safety. |
| W6-05 | Frontend | Implement Role-Aware Authentication Logic | Create UserAdministrationView and protect it with @RolesAllowed("SYSTEM_ADMIN"). | Implemented so that the Regular Staff cannot access Admin View. | Completed | Saturday - July 25, 2026 Implemented strict Role-Aware navigation across the Vaadin frontend. |
| W6-05 | Testing | Authentication Testing | Write unit tests for AppUserDetailsService to prove account state logic. | Login Test for Admin successfully accessed the Dashboard. | Completed | Saturday - July 25, 2026 Ran unit tests to verify that the Spring Security login rejection rules for locked and disabled accounts function flawlessly. |
| W6-05 | Architecture | Exception Foundation | Create standard HTTP exception handlers and define common as an OPEN Modulith. | Let each Module component share exception handlers. | Completed | Saturday - July 25, 2026 Established a shared cross-cutting common module containing standard HTTP exception handlers to automate REST error translation. Resolved Spring Modulith architectural boundary violations by formally declaring the common package as an OPEN module via package-info.java. |

Wednesday - July 22, 2026

- Created Arc Transit System project using Spring Initializr.

- Configured the project with Java 21, Spring Boot 4.1.0, Maven, and the Maven Wrapper.

- Used a temporary project-specific JAVA_HOME configuration (e.g. set cmd command to switch to JDK 21, so the project runs on Java 21) without changing the permanent system-wide Java version. - Verified that Java, javac, Maven, and the Maven Wrapper were using the expected development environment.

  - set "JAVA_HOME=C:\Program Files\Java\jdk-21.0.11"

  - set "PATH=%JAVA_HOME%\bin;%PATH%"

to verify:

  - mvnw.cmd -version

  - javac -version

- Initialized the local Git repository for the new Arc Transit System project.

  - https://github.com/chuckzxxmello/arc-transit.git

- Ran the generated Spring Boot automated test and confirmed that the application context loaded successfully with no test failures.

  - mvnw.cmd -version

  - mvnw.cmd clean test

Thursday - July 23, 2026

- Added the Vaadin dependencies on pom.xml

  - <vaadin.version>25.2.3</vaadin.version>	(check pom.xml for the other configurations)

- Created a simple dashboard route to establish a server-side rendered user interface

  - arctransit\analytics\ui\DashboardView.java

- Recorded the progress via edit.md and README.md to ensure development process are tracked.

- Added the PostegreSQL dependencies on the pom.xml and configured the PostgreSQL to run on a Docker Desktop container via Docker Compose, and successfully connected the Java application to the database on port 5433 & 5432 (the other port for the running Spring Boot application, but the web still uses localhost: 8080).

  - <groupId>org.postgresql</groupId>

  - docker-compose.yaml

- Configured Flyway-managed database schemas (e.g. V1_create_fleet_units.sql), establishing a strict, version-controlled migration that will avoid unpredictable Hibernate auto-ddl behaviors in production environments.

- Implemented Spring Modulith dependencies and established the modular modulith architecture folder layout in the codebase, strictly isolating the application into distinct, cohesive business capability packages (e.g., auth, fleet, analytics).

  - <groupId>org.springframework.modulith</groupId> (-starter-test and -starter-core)

- Designed and implemented the database SQL schema specifically for authentication and user roles, implementing PostegreSQL constraints for lowercase uniqueness and fixed enum-style role mappings on the database.

  - V2__create_authentication_tables.sql

- Created and debugged the initial working authentication login component, ensuring the Vaadin interface correctly interfaces with the 
Spring Security dependency

  - <groupId>org.springframework.boot</groupId
<artifactId>spring-boot-starter-security</artifactId>

- Updated edit.md status to reflect the completion and verification of the entire development process.

Saturday - July 25, 2026 (pushed the project on July 26, 2026 at 1:30 AM)

- Implemented the DevAdminSeeder to automatically bootstrap the default admin account securely via JdbcTemplate when the dev Spring profile is active, removing unsafe SQL seed scripts from the migration history.

  - arc-transit\src\main\java\com\transit\arctransit\auth\security\DevAdminSeeder.java

- Refactored the Authentication module's public API to utilize immutable Java 21 records, for thread safety and eliminating mutable DTO boilerplate.

  - arc-transit\src\main\java\com\transit\arctransit\auth\UserView.java

  - public record UserView (

String username,

String displayName,

String email,

String accountStatus,

Set<String> roles

) {}

- Modernized the AppUser domain entities to enforce strict @Enumerated(EnumType.STRING) constraints for AccountStatus, completely mitigating the risk of raw string typos at runtime.

  - @Enumerated(EnumType.STRING)

@Column(name = "account_status", length = 20, nullable = false)

private AccountStatus accountStatus;

- Fixed critical authentication logic in AppUserDetailsService to accurately evaluate account locking and disabling using null-safe Java Enum equality comparisons.

- Implemented strict Role-Aware navigation across the Vaadin frontend by protecting the UserAdministrationView with Jakarta's @RolesAllowed("SYSTEM_ADMIN") annotation, successfully blocking unauthorized operations staff.

  - arc-transit\src\main\java\com\transit\arctransit\auth\security\AppUserDetailsService.java

  - arc-transit\src\main\java\com\transit\arctransit\auth\ui\UserAdministrationView.java

- Authored highly isolated unit tests utilizing Mockito to conclusively verify that the Spring Security login rejection rules for locked and disabled accounts function flawlessly without requiring the full Spring context.

  - arc-transit\src\test\java\com\transit\arctransit\AuthenticationTests.java

- Established a shared cross-cutting common module containing standard @ResponseStatus HTTP exception handlers to automate REST error translation.

arc-transit\src\main\java\com\transit\arctransit\common\exception:

  - ResourceNotFoundException.java

  - BusinessConflictException.java

  - ResourceNotFoundException.java

- Resolved Spring Modulith architectural boundary violations by formally declaring the common package as an OPEN module via package-info.java, legally permitting exception sharing across isolated business modules.

arc-transit\src\main\java\com\transit\arctransit\common\package-info.java:

  - @org.springframework.modulith.ApplicationModule(

displayName = "Common Shared Library",

type = org.springframework.modulith.ApplicationModule.Type.OPEN

)

- Ran automated test and successfully executed the Maven test suite (cmd -> mvnw clean test), achieving BUILD SUCCESS.

- Updated edit.md status to reflect the completion and verification of the entire development process.

## Week 7 - Driver and Route

| ID | Area | Task | Work Details | Expected Result | Status | Notes / Date |
| --- | --- | --- | --- | --- | --- | --- |
| W7-01 | Database | Add Validation Dependency | Added spring-boot-starter-validation dependency. | Enable runtime enforcement of validation annotations on Java 21 command records. | Completed | Saturday - August 2, 2026 Added the validation starter to ensure annotations are not silently ignored at runtime. |
| W7-02 | Database | Create Drivers Migration | Created Drivers SQL schema Flyway migration for the driver database. | Persist driver records with enforced data integrity at the database level. | Completed | Saturday - August 2, 2026 Followed the exact commenting and constraint patterns established by V1 and V2 migrations. |
| W7-03 | Database | Create Routes Migration | Created Route SQL schema Flyway migration for the driver database. | Store ordered route stops with parent-child relationship and cascade deletion. | Completed | Saturday - August 2, 2026 Foreign key uses ON DELETE CASCADE for parent-child cleanup. |
| W7-04 | Database | Create Dispatch Migration | Created Dispatch SQL schema Flyway migration for the driver database. | Prevent a bus or driver from being assigned twice at the same date and time. | Completed | Saturday - August 2, 2026 Partial indexes allow cancelled assignments to be replaced. |
| W7-05 | Backend | Implement Fleet Module | Built FleetUnit.java entity with @Enumerated(EnumType.STRING), @Version optimistic locking, soft-delete via archivedAt, and domain state transition methods. Enums: VehicleType, OperationalStatus. Repository: FleetUnitRepository.java. | JPA persistence layer for fleet units with status lifecycle management. | Completed | Saturday - August 2, 2026 Domain methods: activate(), deactivate(), markUnderMaintenance(), markOutOfService(), archive(). |
| W7-06 | Backend | Fleet Public API | Created FleetUnitView, FleetUnitSummaryView, CreateFleetUnitCommand, UpdateFleetUnitCommand, FleetUnitQuery as immutable Java 21 records. FleetManagementService interface as Modulith API boundary. | Expose fleet operations through a clean public API without leaking domain internals. | Completed | Saturday - August 2, 2026 The DTOs are set to be immutable records enforcing Spring Modulith boundaries. |
| W7-07 | Backend | Fleet Service Layer | Implemented AppFleetManagementService.java with input normalization (uppercase, trimmed), uniqueness validation, @PreAuthorize method-level security, and @Transactional management. | Enforce business rules and role-based access on all fleet operations. | Completed | Saturday - August 2, 2026 Method security restricts mutations to authorized roles only. |
| W7-08 | Frontend | Fleet Vaadin View | Implemented FleetManagementView.java at route /fleet with Grid, Dialog-based create/edit forms, status change ComboBox, and archive button. | Provide a full CRUD interface for managing fleet units through the browser. | Completed | Saturday - August 2, 2026 Uses Vaadin Grid, Dialog, and ComboBox components. |
| W7-09 | Backend | Implement Driver Module | Built Driver.java entity with isLicenseExpired() method comparing licenseExpiryDate against LocalDate.now(). Enums: EmploymentStatus, LicenseType. Repository: DriverRepository.java. | JPA persistence layer for drivers with license expiry detection. | Completed | Saturday - August 2, 2026 License expiry is computed dynamically, not stored as a static flag. |
| W7-10 | Backend | Driver Public API | Created DriverView, DriverSummaryView (with licenseExpired boolean flag), CreateDriverCommand, UpdateDriverCommand, DriverQuery, DriverManagementService interface. | Expose driver operations through a clean public API with expiry awareness. | Completed | Saturday - August 2, 2026 DriverSummaryView includes a computed licenseExpired field. |
| W7-11 | Backend | Driver Service Layer | Implemented AppDriverManagementService.java with employee number and license number uniqueness validation. | Enforce unique employee and license identifiers across all drivers. | Completed | Saturday - August 2, 2026 Prevents duplicate registrations at the service layer. |
| W7-12 | Frontend | Driver Vaadin View | Implemented DriverManagementView.java at route /drivers with a visual red "EXPIRED" badge for expired licenses, DatePicker for license expiry input. | Provide a CRUD interface with clear visual indicators for expired licenses. | Completed | Saturday - August 2, 2026 Uses Vaadin DatePicker and Span badge for visual license status. |
| W7-13 | Backend | Implement Route Module | Built Route.java entity with @OneToMany(cascade = ALL, orphanRemoval = true) for RouteStop child entities, @OrderBy("stopSequence ASC"), and replaceStops() for atomic stop replacement. | JPA parent-child persistence for routes and their ordered stops. | Completed | Saturday - August 2, 2026 Atomic stop replacement ensures consistency during updates. |
| W7-14 | Backend | Route Public API | Created RouteView, RouteSummaryView, RouteStopView, CreateRouteCommand (with nested StopEntry record), UpdateRouteCommand, RouteQuery, RouteManagementService. | Expose route operations with ordered stop data through a clean public API. | Completed | Saturday - August 2, 2026 CreateRouteCommand uses nested StopEntry records for ordered stop input. |
| W7-15 | Backend | Route Service Layer | Implemented AppRouteManagementService.java with ordered stop management. | Enforce route business rules and manage stop ordering during create/update. | Completed | Saturday - August 2, 2026 Handles stop sequence validation and atomic replacement. |
| W7-16 | Frontend | Route Vaadin View | Implemented RouteManagementView.java at route /routes with dynamic stop list management in create/edit dialogs. | Provide a CRUD interface for managing routes and dynamically adding/removing stops. | Completed | Saturday - August 2, 2026 Stop list is editable inline within the dialog before submission. |

Saturday - August 1, 2026

- Added the spring-boot-starter-validation dependency to pom.xml to enable Jakarta Bean Validation (@NotBlank, @Size, @Valid) on command records.

  - <groupId>org.springframework.boot</groupId>

  - <artifactId>spring-boot-starter-validation</artifactId>

- Created the V3 Flyway migration (V3__create_drivers.sql) for the arc.drivers table, implementing detailed comments and named database constraints.

  - arc-transit\src\main\resources\db\migration\V3__create_drivers.sql

- Created the V4 Flyway migration (V4__create_routes_and_stops.sql) with arc.routes and arc.route_stops tables.

  - arc-transit\src\main\resources\db\migration\V4__create_routes_and_stops.sql

- Created the V5 Flyway migration (V5__create_dispatch_assignments.sql) with partial unique indexes.

  - arc-transit\src\main\resources\db\migration\V5__create_dispatch_assignments.sql

- Implemented the Fleet module with full JPA persistence, enums, repository, services, and Vaadin view.

  - arc-transit\src\main\java\com\transit\arctransit\fleet

- Implemented the complete Driver module with license expiry checking and visual expired badge.

  - arc-transit\src\main\java\com\transit\arctransit\driver

- Implemented the complete Route module with parent-child JPA relationship for ordered stops.

  - arc-transit\src\main\java\com\transit\arctransit\route

- Implemented the complete Dispatch module with cross-module validation and lifecycle state machine.

  - arc-transit\src\main\java\com\transit\arctransit\dispatch

Sunday - August 2, 2026

- Removed hardcoded admin credential insertion from V2__create_users.sql and created AdminUserInitializer.java with Spring @Value property injection.

  - arc-transit\src\main\java\com\transit\arctransit\auth\AdminUserInitializer.java

- Resolved Spring Modulith architectural boundary violations caused by cyclic dependencies. Moved MainLayout.java to common.ui.

  - arc-transit\src\main\java\com\transit\arctransit\common\ui\MainLayout.java

- Fixed UI layout defects in MainLayout: centered search bar and prevented clock wrapping.

  - arc-transit\src\main\java\com\transit\arctransit\common\ui\MainLayout.java

- Refactored DashboardView.java with live Grid tables, OpenStreetMap IFrame (Cavite), and SplitLayout detail panel.

  - arc-transit\src\main\java\com\transit\arctransit\analytics\ui\DashboardView.java

- Implemented UserAdministrationView.java restricted exclusively to SYSTEM_ADMIN for testing account creation via PasswordEncoder.

  - arc-transit\src\main\java\com\transit\arctransit\auth\ui\UserAdministrationView.java

- Integrated hardDeleteUnit, hardDeleteDriver, and hardDeleteRoute into ArchiveView for SYSTEM_ADMIN roles only.

  - arc-transit\src\main\java\com\transit\arctransit\analytics\ui\ArchiveView.java

## Week 8 - Dispatch and Assignment

| ID | Area | Task | Work Details | Expected Result | Status | Notes / Date |
| --- | --- | --- | --- | --- | --- | --- |
| W8-01 | Architecture | Configure Dispatch Dependencies | Updated dispatch/package-info.java with allowedDependencies = {"fleet", "driver", "route", "common"} for Spring Modulith cross-module access. | Formally declare cross-module references instead of using Type.OPEN. | Completed | Saturday - August 1, 2026 Follows Spring Modulith best practices for explicit dependency declarations. |
| W8-02 | Backend | Implement Dispatch Domain | Built DispatchAssignment.java entity using FK-by-ID pattern (plain Long IDs). State machine methods: startTrip(), completeTrip(), cancel(). Enum: DispatchStatus. Repository: DispatchAssignmentRepository.java. | Full JPA persistence layer for dispatch assignments with lifecycle state machine. | Completed | Saturday - August 1, 2026 FK-by-ID pattern respects module boundaries by avoiding @ManyToOne cross-module references. |
| W8-03 | Backend | Dispatch Public API | Created DispatchAssignmentView (includes resolved display names), CreateDispatchCommand, DispatchQuery, DispatchService interface. | Expose dispatch operations through a clean public API boundary. | Completed | Saturday - August 1, 2026 View records include resolved bus/driver/route names for display. |
| W8-04 | Backend | Dispatch Service Layer | Implemented AppDispatchService.java with 5-step cross-module validation: (1) fleet unit ACTIVE, (2) driver ACTIVE + license valid, (3) route ACTIVE, (4) no bus overlap, (5) no driver overlap. | Enforce all cross-module business rules before creating a dispatch assignment. | Completed | Saturday - August 1, 2026 Uses public service interfaces for cross-module entity lookup. |
| W8-05 | Frontend | Dispatch Vaadin View | Implemented DispatchView.java at route /dispatch with ComboBox dropdowns for active entities and context-aware action buttons. | Provide a dispatch management interface with filtered entity selection. | Completed | Saturday - August 1, 2026 Action buttons change based on current dispatch status (state machine). |
| W8-06 | Security | Secure Admin Credentials | Removed hardcoded admin credential insertion from V2__create_users.sql. Created AdminUserInitializer.java with Spring @Value property injection for secure first-boot user creation. | Create the SYSTEM_ADMIN user dynamically on first boot via environment variables. | Completed | Sunday - August 2, 2026 Supports environment variable overrides for production deployment. |
| W8-07 | Architecture | Resolve Cyclic Dependencies | Moved MainLayout.java to com.transit.arctransit.common.ui and refactored Vaadin SideNavItem definitions to use raw string routes instead of class imports. | Sever the module cycle and pass Spring Modulith boundary validation. | Completed | Sunday - August 2, 2026 Completely eliminated cross-module class imports in navigation. |
| W8-08 | Frontend | Dashboard Live Integration | Fixed UI layout defects in MainLayout. Replaced static placeholders in DashboardView with live Grid tables, an OpenStreetMap IFrame (Cavite region), and a SplitLayout detail panel. | Present a functional, live-integrated, interactive dashboard to operations staff. | Completed | Sunday - August 2, 2026 Connected RouteManagementService and FleetManagementService directly to UI components. |
| W8-09 | Security | User Administration CRUD | Implemented UserAdministrationView.java restricted exclusively to SYSTEM_ADMIN. Full CRUD with CreateUserCommand to create OPERATIONS_STAFF accounts via PasswordEncoder. | Allow administrators to dynamically create and manage staff testing accounts. | Completed | Sunday - August 2, 2026 Passwords are hashed with BCrypt before database storage. |
| W8-10 | Backend | Hard Deletion for Archives | Integrated hardDeleteUnit, hardDeleteDriver, and hardDeleteRoute into their respective modules. Exposed via "Permanently Delete" buttons in ArchiveView for SYSTEM_ADMIN only. | Enable permanent removal of archived entities with confirmation prompts. | Completed | Sunday - August 2, 2026 All deletions backed by Vaadin ConfirmDialog to prevent accidental data loss. |
| W8-11 | Auditing | Cross-Module Audit Logging | Created V8__create_audit_logs.sql, AuditLog.java entity, AuditLogRepository.java, AuditRecordingService.java interface, and AppAuditRecordingService.java. Injected into all primary module services. | Track and persist business actions as an append-only audit ledger across all modules. | Completed | Monday - August 3, 2026 entity_id is plain BIGINT (no FK) to prevent constraint violations during hard deletes. Uses SecurityContextHolder for action attribution. |
| W8-12 | Database | Dispatch Archive and Migration Fixes | Created V7__add_dispatch_archive.sql adding archived_at TIMESTAMPTZ column. Corrected Flyway migration sequence collisions (V6, V7, V8). Fixed save() vs saveAndFlush() timing. | Support soft-deletion of completed trips and ensure reproducible schema deployments. | Completed | Monday - August 3, 2026 Standardized migration ordering prevents sequence collisions across environments. |
| W8-13 | Frontend | Dashboard Real Data and Diagnostics | Integrated dashboard summary cards with live module service queries. Made cards clickable. Developed StartupDiagnosticRunner to log entity counts on boot. | Verify runtime module interactions and display real-time operational metrics. | Completed | Monday - August 3, 2026 Dashboard cards route directly to /fleet, /drivers, /routes, /dispatch views. |
| W8-14 | Testing | Unit Tests for All Services | Created JUnit 5 and Mockito tests for AppFleetManagementService, AppDriverManagementService, AppRouteManagementService, and AppDispatchService. | Verify all cross-module validations, unique constraints, and state transitions. | Completed | Monday - August 3, 2026 Covers create, update, archive, status transitions, and error cases. |
| W8-15 | Testing | Auth Integration Test | Engineered AuthDebugIT.java (@SpringBootTest) exercising AppUserDetailsService.loadUserByUsername(). Adjusted PostgreSQL credentials for test environment. | Validate that database role mappings produce correct Spring Security GrantedAuthority objects. | Completed | Monday - August 3, 2026 Confirmed ROLE_SYSTEM_ADMIN authority is correctly resolved from database. |
| W8-16 | Verification | Full Build Verification | Ran mvnw clean test confirming all unit tests and context loads succeed under Java 21. | Achieve BUILD SUCCESS with zero test failures. | Completed | Monday - August 3, 2026 Closes out all remaining Week 8 structural deliverables. |
| W8-17 | Documentation | Update Project Logs | Updated edit.md with full Week 7/8 implementation log. Created Kanban progress tracker tables. | Ensure development process is tracked and documented for review. | Completed | Monday - August 3, 2026 Detailed logs include online documentation references and file paths. |

Monday - August 3, 2026

- Implemented complete cross-module Audit Logging System (V8__create_audit_logs.sql, AuditLog entity, repository, AppAuditRecordingService).

  - arc-transit\src\main\resources\db\migration\V8__create_audit_logs.sql

  - arc-transit\src\main\java\com\transit\arctransit\audit

- Constructor-injected AuditRecordingService into all primary module services.

  - AppFleetManagementService.java

  - AppDriverManagementService.java

  - AppRouteManagementService.java

  - AppDispatchService.java

- Created V7__add_dispatch_archive.sql for soft-deletion of completed trips.

  - arc-transit\src\main\resources\db\migration\V7__add_dispatch_archive.sql

- Resolved transaction timing issues across integration tests by explicitly distinguishing save() vs saveAndFlush().

  - arc-transit\src\main\java\com\transit\arctransit\auth\application\AppUserAdministrationService.java

- Integrated dashboard summary cards with live data and developed StartupDiagnosticRunner.

  - arc-transit\src\main\java\com\transit\arctransit\analytics

- Created comprehensive JUnit 5 and Mockito tests for all primary management services and engineered AuthDebugIT.java.

  - arc-transit\src\test\java\com\transit\arctransit

- Ran mvnw clean test confirming all unit tests and context loads succeed under Java 21 (BUILD SUCCESS).

# 6. Full 12-Week Gantt Chart

| Workstream | Timeline | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Scope and requirements | June 15 - 21, 2026 | ✓ |  |  |  |  |  |  |  |  |  |  |  | Completed |
| Architecture and UX design | June 22 - 28, 2026 |  | ✓ |  |  |  |  |  |  |  |  |  |  | Completed |
| Database design | June 29 - July 5, 2026 |  |  | ✓ |  |  |  |  |  |  |  |  |  | Completed |
| Application-service contracts | July 6 - 12, 2026 |  |  |  | ✓ |  |  |  |  |  |  |  |  | Completed |
| Application foundation | July 13 - 19, 2026 |  |  |  |  | ✓ |  |  |  |  |  |  |  | Completed |
| Security, audit, and Fleet | July 20 – 26, 2026 |  |  |  |  |  | ✓ |  |  |  |  |  |  | Completed |
| Driver and Route | July 27 - August 2, 2026 |  |  |  |  |  |  |  |  |  |  |  |  | In Progress |
| Dispatch and assignment | August 2 – August 9, 2026 |  |  |  |  |  |  |  |  |  |  |  |  | In Progress |
| Incident and Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  | Planned |
| Status and analytics |  |  |  |  |  |  |  |  |  |  |  |  |  | Planned |
| Testing and benchmarks |  |  |  |  |  |  |  |  |  |  |  |  |  | Planned |
| Deployment and release |  |  |  |  |  |  |  |  |  |  |  |  |  | Planned |
| Documentation |  |  |  |  |  |  | ✓ |  |  |  |  |  |  | In Progress |